## Sayfa1
Start Date 7/10/2024
Week |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Procedural Steps | Current State | 4 October 2024 | 11 October 2024 | 18 October 2024 | 25 October 2024 | 1 November 2024 | 8 November 2024 | 15 November 2024 | 22 November 2024 | 29 November 2024 | 6 December 2024 | 13 December 2024 | 20 December 2024 | 27 December 2024 | 3 January 2025 | 10 January 2025 | 17 January 2024
Team Setup | Completed | bar: 1 to 3
Project Proposal Form | Completed | bar: 2 to 3
Project Selection Form | Completed | bar: 2 to 3
Project Work Plan | Completed | bar: 3 to 4
Literature Review | Continuing | bar: 4 to 6
Software Requirements Specification | Continuing | bar: 6 to 10
Project Resort | Continuing | bar: 9 to 12
Software Design Description | Continuing | bar: 11 to 13
Project Report | Continuing | bar: 14 to 15
Presentation | Continuing | bar: 16